## Sheet1
Task | Member | Start Date | End Date | Time Needed
Plan Project | Graysen | 2024-11-29 | 2024-11-30 | 1
Literature Research | Ken | 2024-11-30 | 2024-12-01 | 1
Create / Evaluate First Model | Ken | 2024-12-01 | 2024-12-03 | 2
Create / Evaluate Second Model | Graysen | 2024-12-02 | 2024-12-04 | 2
Write Video Script | Graysen | 2024-12-04 | 2024-12-06 | 2
Flim Video | Ken | 2024-12-06 | 2024-12-09 | 3
Edit Video | Graysen | 2024-12-06 | 2024-12-09 | 3

## Sheet2
Task | Member | Start Date | End Date | Days Needed
Plan Project | Graysen | 45625 | 2024-11-30 | 1
Literature Research | Ken | 45626 | 2024-12-01 | 1
Create / Evaluate First Model | Ken | 45627 | 2024-12-03 | 2
Create / Evaluate Second Model | Graysen | 45628 | 2024-12-04 | 2
Write Video Script | Graysen | 45630 | 2024-12-06 | 2
Flim Video | Ken | 45632 | 2024-12-09 | 3
Edit Video | Graysen | 45632 | 2024-12-09 | 3